## Iteration Plan
RED: Task removed BLUE: Task completed GREEN: New task introduced PURPLE and BOLD: Needs attention PINK: Next Task that can be taken up(Tanmeet) Cell Highlighted in Yellow: Completed/Near completion
| User Story | Task | Definition |  | Comments by Tanmeet | Status
1 | Based on the role, user can login to the dedicated screen | -Profile form for all employees -Create user login screen -Create Employee DB -Link user profiles to the login screen -Add functionality to add new user account - Add functionality to help button(all screens) -Add functionality to logout the user from the system | Note: There are four type of users: Supervisor, Receiving staff, Technician, Help Desk Staff | Back: Data entered matches the database and directs the user to the Main page of the respective role | Supervisor can directly add new user, remove the button to request new user | -Done
2 | Receiving Staff can view all the issued RMAs(new) | -Connect CSM DB to fetch all the RMA# -Design layout for the Receiving Staff screen -Code to link the receiving screen with CSM to produce list of all incoming RMAs(Open RMAs) -DB connection to produce list of RMAs received and on wait. -Activate Refresh button to update RMA lists(Open and Received, Waiting List) -Enable radio Buttons, connect to DB | Note: Number generated by CSM system | Back: Status is automatically updated to ‘ Open’ |  | -Done With Dummy Data for RMA Table
3 | Receiving Staff can update Status to Received, Wait, Close | -Add items to drop down list(Status accessible to receiving staff) -Code to add functionality to 'update' button to update the database -Code to record/track dates for ' Wait' and 'Received' status -Code to send out email notifications,wherever applicable, based on dates criteria -DB connection to RMA table for above | Note: As soon as the product comes in, status is required to be changed to `received` | Back: As soon as the status is updated, the date is automatically recorded. Supervisor is notified if the status remains same for >=3 days. | For received | -Update button enabled successfully. -Pending: Logic to record dates, in order to send out the email notifications to concerned person.
|  |  | Note: Only after the product is verified and sent back to client | Back: Supervisor is notified to follow up with client if the status remains ‘Wait’ for >= 20 working days. | For Wait
|  |  | Note: Repair/Replace request? | Back: DB is updated with the tracking number. Request archived. | For Close
4 | Technician can receive notifications | -Design Technician Screen Layout -Activate message box, link employee profiles -Link the message box to the table 'new requests' -DB connection - link RMA# in the 'new requetss' table to autofill the availble fields in update section | Note: Every time new request is assigned | Back: Email Notification is sent. |  | -Only the mentioned tasks left
5 | Technicians can be assigned Wos | -Connect WO queue to the message box and 'new request'list -Add functionality to each list item to prompt to 'Proceed' window. -Code to add functionality to 'accept' button and link it to the 'active Technician WOs' table -DB connection to status table and RMA request to record above - Code to track dates for ' Assigned' Status -Code to send out email notifications | Note: Automatic assignment of the requests by the system. There are two types of requests: Replace/Repair or Refund. | Back: Status is updated in database to ‘Assigned’. Supervisor is notified if the status remains same for >=5 days. | After the request is acceptd by theTech, what would be the chnge in status ? Suggestion: Until the request is accepted by the tech, the status remains 'waiting to be assigned'.Once accpeted it is changed to 'assigned' and added in Tech WO queue
6 | Technicians can delegate requests | -Code to add functionality to ' delegate' button(both on Prceed Window & update screen) and further link it to 'update message' prompt window -Create DB for various information sections like resolution,description etc -DB connection to the Status update section with the prompt window. -Add functionality to automatically record the dates when user enters information in status update section. -Code to send notification to Supervisor, asking for approval/putting the request on 'hold' | Note: Press button ’delegate’, against the RMA#. Reason for delegation with date, to be specified in Status Updates section | Back: Prompt user to fill in the status update section. System to automatically change the status to “Hold’. Email notification to be sent to the supervisor for manual assignment of the work order. |  | -To reach to Proceed window, automated request assignment is needed --> how ?
7 | Technicians can view their WO queue | -Design Layout for the Table showing Technician WO details -DB connection to view current assigned request - link RMA# in the WO table to autofill the availble fields in update section | Note: Only the ones assigned to them | Back: Data displayed reflects current Technician WO queue stored in DB
8 | Technician can put the request on 'Hold' | -Link each drop-down list item(in 'update status' section) to the status table -Code to add functionality to 'update' button to update the database -Code to promt a window to enter reason as soon as the status is changed to 'Hold' -DB connection to the Status update section with the prompt window. -Code to record/track dates for 'Hold' status -Code to send out email notifications -DB connection to status table and RMA request for above | Note: Only when there is internal wait on part or a priority task comes in. | Back: Email notification to be sent to the supervisor at once to take the appropriate action.
9 | Technician can update status to 'completed' | -Code to prompt a window to confirm if the product was fixed or not -DB connection to the Status update section with the prompt window. -Code to send out completion notifications -DB connection to status table and RMA request for above |  | Back: Prompt user to fill in Resolution Section and confirm if the order was fixed or not.
10 | Technicians can open requests to edit/update it | -Layout for the 'Open' screen -Code to link the 'open' button to this screen and back to the Technician screen | Note: Open request to view sub-statuses OR to make changes to it | Back: Opens page, to update notes and sub-status of the request. |  | Done! Cover rest in User Story 11
11 | Technicians can maintain Sub-Statuses | - Document Business Logic -Code to maintan count of required sub-status for each request(based on number of pieces) -Create interface for the sub-statuses -Create DB for Sub-statuses -Document sub-states Definition -Add functionality to save all the sub-statuses in DB using save button. -Code RMA status to supersede all the sub-statues of a particular request. -Link comments section with each sub-statues -DB connection for above | Note: Only in case where RMA consists of more than 1 product to be fixed. | Back: RMA status supersedes the sub-statuses.
12 | Supervisor can receive notifications | -Design Supervisor Screen Layout -Activate message box, link employee profile -Link the message box to the tables 'new requests' and ' request on hold' - link RMA# in both the tables to autofill the availble fields in update section -DB connection | Note: Every time new request is assigned or request is put on hold. | Back: Email Notification is sent.
13 | Supervisor can edit all the active requests | -Code to all the inputs fields to accept values manually and also fetch data(except RMA#) from the DB, wherever available. -Link each drop-down list item(in 'update status' option) to the status table -Code to prompt a window to update the appropriate reason for status change. -Code to link the 'open' button to the 'open' screen and back to the Supervisor screen -Code to add functionality to 'open' button to view the complete request information(on ' Open Page') and make the changes.(Similar to Tech Open Page) -Code to add functionality to ' Update' button to reflect the changes in the DB. -DB connection | Note: Provided appropriate status updates are done | Back: Changes reflected in DB. |  | '- Issue: 'Go Back' button(on Tech_open screen) doesnot not work for more than once!! -Done!! Cover Open Screen in User story 11
14 | Supervisor can view sub-statuses under all RMA request. | -Access to the ' Open page' same as above page |  | Back: Data displayed reflects current data in the DB |  | Done
15 | Supervisor can view WO queue and priortize it as per the need. | -Code to generate the WO queue arranged in order of date -Connect the 'View WOs in queue' button to the screen displaying WO queue. -Code to allow the user to change the order of the WOs as per the need and re-generate the WO queue. -DB connection -Link 'WO queue' page, back to the Supervisor Screen | Note: Primarily WOs are arranged in order of the dates assigned. The order can be modified as per the user need. | Back: Queue refreshed as per the requested priority
16 | Supervisor can assign WOs to the technician | -Link the 'Techname' label to the Technicain DB to view the current assigned Tech. -Add functionality to the 'Change' button to change/ assign new tech to the WO. -Add functionality to 'Update' button to reflect the changes in the DB. -Add button to ' WO queue' page and code it for the assignment of the Technician against a new WO(currently not assigned by the system) - Link the assigned WO to send the notification to the assigned technician. -DB connection | Note: Supervisor can assign Technician: -If the request is on Hold OR in case of priority task assignment. - Directly from the WO queue | Back: Updates Technician WO queue. |  | - Need to work on the WO queue(How??)and duplicate the technician assignment functionality.
17 | Supervisor can assign category against each RMA request | -Business logic to categorize WO on the basis of number of pieces. -Code to assign categories to each request, if quantity provided. - Link the radio buttons to the 'Category' table -Enable radio buttons to choose the desired category and link it to the request. -Add functionality to 'Update' button to reflect the changes in the DB. | Note: -Software can categorize on the basis of number of pieces. -User can manually change the category as well. | Back: -Category stored in DB. -Requests queued up for assignment and automatically assigned considering category and appropriate tags. |  | -How to run a SQL Server Script in Visual to auto fill the Category field based on the quantity?
18 | Supervisor can split current RMA request into parts | -Logic to assign sub-RMA numbers and associated information with each one of them -Design screen(Split RMA) layout for splitting the RMA -Link 'Split RMA' button to direct to 'Split RMA' page. -Code to genearte new RMA numbers. -Code to link the associated information with the newly generated RMAs. -DB connection | Note: Only in case where the fixed products are sent to client in segments rather than waiting for the order to be sent at once. | Back: RMA request split into parts by appending with consecutive alphabets and separate status for the request(making it an individual request) maintained in DB |  | -High-level plan so far!!! Requires further discussion to implement this section.
19 | Supervisor can receive Alerts |  |  | Back: Daily/Weekly alerts via reports are sent via email. Data displayed reflects the current data in DB, highlighting the items that need attention | yet to be decied, as to how and when are we going to do it : send emails or daily/weekly reports?
20 | Supervisor can generate reports | -Enable filter options(Date, Client Name, Status) using radio buttons -Connect the database tables with the respective filter option -Code to generate the reports and link its functionality to'Generate report' button. -Add functionality to view the details and link it to ' View All WOs' button. -DB connection | Note: Based on selected parameters | Back: Reports generated as per data stored in DB and requested filter. |  | Work with the formating… reports generated!!
21 | Supervisor manages Staff- add/delete/view Employee Info | -Design Form to add employee information -Add functionality to 'Add button' to save new employee information in the db. -Connect DB to EmployeeID and Employee Name -Code to display information by using 'View Info' button, based on the search performed for the Employee. -Code to delete Employee information, by using 'Delete Tech' button, based on the search performed -Code to edit the Employee information, by using ' Edit Info' button, based on the serach performed -Validations on the fields, while adding/updating new employee record -Auto Generated Employee ID | Note: Add new technicians or edit/delete current technician’s profile. | Note: Add new technicians or edit/delete current technician’s profile. | -DONE -Validation- required field validation done ** need to allow the cancel option without entring details** | Done!
22 | Supervisor can Authorize/De-authorize rights to user | -Link the Combo Box to the Help Desk Staff - Add functionality to 'Authorize ' button to link authorized user and allow them access to Update Details(Same as Supervisor) -Code to Authorize users to perform updates tasks(same as Supervisor) -Functionality to remove access against authorized user. | Note: Help Desk staff can be share update tasks with Supervisor for the RMAs during heavy workload or his absence. | Back: Enable the `Update Details` section for the authorized user. |  | Not sure how to implement Authorize button functionality
23 | Help Desk Staff can assign the WOs to Technician | - Enable access to the authorized users to perform Update tasks similar to those of Supervisor | Note: Only authorized users. If the request is on Hold OR in case of priority task assignment | Back: Updates Technician WO queue.
24 | All users can view details of any valid RMA# | -Link/Create DB for all the product items -Link/Create DB for all the customers -Create DB for all RMA statuses -Documentation of all status definition -Design Layout for the Table showing details -Code to link the 'view deatils' button to the desired table to be shown -DB connection for above |  | Back: Data displayed reflects current data stored in DB
25 | All users can search for an RMA# | -Design layout for Search Screen -Define criteria for searching(use of filters) -SQL statements to produce desired table with search results -Code to implement search and produce results -DB connection |  | Back: Search by: -RMA# -Client name -Date -Status |  | -Done! - Issue: 'Go Back' button on Search Screen
26 | All users can view history of any previous RMA request(closed RMA) | -Design layout for the Notes section -DB connection of the closed RMA request to 'view history' button -Code to activate the View button , only when deatils are requested for any request (a closed RMA request). -Code to link the 'view history' button to produce history (from Notes section) for the requested RMA# request -Add ' Edit' button, to enable changes in Notes section |  | Back: Notes section is displayed. |  | -Done -CHECK PARAMETER SIZES against column sizes to allow more space for the data entered. -What would be the appropriate datatype ?
27 | All users can manually update the information in Resolution, description, comments, status updates sections. | - Link ' Edit' button in notes to the Database of individual information sections:Resolution, description, comments,status update. -Add functionality to 'Update' button to reflect the changes in the DB. -Code to record the date and user name, updating the sections -DB connection |  | Back: DB updated. Records date and name of user updating the field

## UserStories
| User Story | Definition
1 | Based on the role, user can login to the dedicated screen | Note: There are four type of users: Supervisor, Receiving staff, Technician, Help Desk Staff | Back: Data entered matches the database and directs the user to the Main page of the respective role
2 | Receiving Staff can view all the issued RMAs(new) | Note: Number generated by CSM system | Back: Status is automatically updated to ‘ Open’
3 | Receiving staff can change the status to ’Received’ | Note: As soon as the product comes in, status is required to be changed to `received` | Back: As soon as the status is updated, the date is automatically recorded. Supervisor is notified if the status remains same for >=3 days.
4 | Receiving staff can put the request on Waiting status | Note: Only after the product is verified and sent back to client | Back: Supervisor is notified to follow up with client if the status remains ‘Wait’ for >= 20 working days.
5 | Receiving staff can close the request | Note: Repair/Replace request? | Back: DB is updated with the tracking number. Request archived.
6 | Technician can receive notifications | Note: Every time new request is assigned | Back: Email Notification is sent.
7 | Technicians can be assigned Wos | Note: Automatic assignment of the requests by the system. There are two types of requests: Replace/Repair or Refund. | Back: Status is updated in database to ‘Assigned’. Supervisor is notified if the status remains same for >=5 days.
8 | Technicians can delegate requests | Note: Press button ’delegate’, against the RMA#. Reason for delegation with date, to be specified in Status Updates section | Back: Prompt user to fill in the status update section. System to automatically change the status to “Hold’. Email notification to be sent to the supervisor for manual assignment of the work order.
9 | Technicians can view their WO queue | Note: Only the ones assigned to them | Back: Data displayed reflects current Technician WO queue stored in DB
10 | Technician can put the request on 'Hold' | Note: Only when there is internal wait on part or a priority task comes in. | Back: Email notification to be sent to the supervisor at once to take the appropriate action.
11 | Technician can update status to 'completed' |  | Back: Prompt user to fill in Resolution Section and confirm if the order was fixed or not.
12 | Technicians can open requests to edit/update it | Note: Open request to view sub-statuses OR to make changes to it | Back: Opens page, to update notes and sub-status of the request.
13 | Technicians can maintain Sub-Statuses | Note: Only in case where RMA consists of more than 1 product to be fixed. | Back: RMA status supersedes the sub-statuses.
14 | Supervisor can receive notifications | Note: Every time new request is assigned or request is put on hold. | Back: Email Notification is sent.
15 | Supervisor can edit all the active requests | Note: Provided appropriate status updates are done | Back: Changes reflected in DB.
16 | Supervisor can view sub-statuses under all RMA request. |  | Back: Data displayed reflects current data in the DB
17 | Supervisor can view WO queue and priortize it as per the need. | Note: Primarily WOs are arranged in order of the dates assigned. The order can be modified as per the user need. | Back: Queue refreshed as per the requested priority
18 | Supervisor can assign WOs to the technician | Note: Supervisor can assign Technician: -If the request is on Hold OR in case of priority task assignment. - Directly from the WO queue | Back: Updates Technician WO queue.
19 | Supervisor can assign category against each RMA request | Note: -Software can categorize on the basis of number of pieces. -User can manually change the category as well. | Back: -Category stored in DB. -Requests queued up for assignment and automatically assigned considering category and appropriate tags.
20 | Supervisor can split current RMA request into parts | Note: Only in case where the fixed products are sent to client in segments rather than waiting for the order to be sent at once. | Back: RMA request split into parts by appending with consecutive alphabets and separate status for the request(making it an individual request) maintained in DB
21 | Supervisor can receive Alerts |  | Back: Daily/Weekly alerts via reports are sent via email. Data displayed reflects the current data in DB, highlighting the items that need attention
22 | Supervisor can generate reports | Note: Based on selected parameters | Back: Reports generated as per data stored in DB and requested filter.
23 | Supervisor maintains Technician profile | Note: Add new technicians or edit/delete current technician’s profile. | Note: Add new technicians or edit/delete current technician’s profile.
24 | Supervisor can Authorize rights to user | Note: Help Desk staff can be share update tasks with Supervisor for the RMAs during heavy workload or his absence. | Back: Enable the `Update Details` section for the authorized user.
25 | Help Desk Staff can assign the WOs to Technician | Note: Only authorized users. If the request is on Hold OR in case of priority task assignment | Back: Updates Technician WO queue.
26 | All users can view details of any valid RMA# |  | Back: Data displayed reflects current data stored in DB
27 | All users can search for an RMA# |  | Back: Search by: -RMA# -Client name -Date -Status
28 | All users can view history of any previous RMA request(closed RMA) |  | Back: Notes section is displayed.
29 | All users can manually update the information in Resolution, description, comments, status updates sections. |  | Back: DB updated. Records date and name of user updating the field

## WireFrame
RMA Software- Wireframe